# Work Breakdown Structure (WBS)

## Factory Management System for Fresh Fruit Juice Production Factory

Project duration: October 2025 – August 2026 (11 months)

Method: Iterative/incremental SDLC — core skeleton first, then module increments, then integration and hardening.

## 1. Phase 1 — Project Initiation & Requirements (Oct – Nov 2025)

| WBS | Work package | Tasks | Deliverable | Effort |
| --- | --- | --- | --- | --- |
| 1.1 | Background study | Visit/interview juice-factory workflow (procurement → production → QC → sales); identify pain points of paper-based records | Study notes | 16 h |
| 1.2 | Problem & objective definition | Define problem statement, objectives, scope, benefits | Project charter section | 8 h |
| 1.3 | Requirements elicitation | List functional needs per department (stores, production, QA, sales, accounts, maintenance, safety) | Requirement catalogue | 20 h |
| 1.4 | SRS writing | Write IEEE-style SRS (users, FR-5.1…5.16, NFRs, HW/SW, reports) | Software Requirements Specification | 24 h |
| 1.5 | Feasibility & tooling | Evaluate XAMPP/PHP/MySQL vs alternatives; confirm offline LAN capability | Tool decision record | 8 h |

## 2. Phase 2 — System Design (Nov 2025 – Jan 2026)

| WBS | Work package | Tasks | Deliverable | Effort |
| --- | --- | --- | --- | --- |
| 2.1 | Architecture design | Front-controller MVC; route map ?route=module/action; layer responsibilities | Architecture diagram (project chapter) | 16 h |
| 2.2 | Database design | Normalise to 3NF; 38 tables; PK/FK graph around production_batches; ENUM status vocabularies; indexes on FK/date columns | database/freshjuice.sql | 32 h |
| 2.3 | RBAC matrix design | 8 roles × 31 modules × access levels (full/view/own/participate/report/no) | backend/config/permissions.php | 12 h |
| 2.4 | Security design | Session policy, CSRF scheme, bcrypt, audit trail, upload containment | Security section of project chapter | 10 h |
| 2.5 | UI/UX prototype | Glass-theme layout, sidebar IA, KPI dashboard mockups, form patterns | Prototype document | 20 h |

## 3. Phase 3 — Environment & Skeleton (Jan – Feb 2026)

| WBS | Work package | Tasks | Deliverable | Effort |
| --- | --- | --- | --- | --- |
| 3.1 | Dev environment | Install/configure Apache, PHP 8.2, MySQL; project scaffold | Running skeleton | 8 h |
| 3.2 | Framework-less MVC core | Router, base Model (PDO, prepared statements), base Controller (render/getInput/redirect), helpers (sanitize, setFlash, csrfField, generateId) | Core classes | 24 h |
| 3.3 | Auth subsystem | Login/logout, rate limiting, password reset with expiring tokens, session hardening, forgot/reset pages | Working login | 20 h |
| 3.4 | Layout & navigation | Responsive Bootstrap 5 glass theme, role-aware sidebar, flash messages | Master layout | 16 h |

## 4. Phase 4 — Module Development (Feb – Jun 2026)

Each work package = model + controller + views + seed data + CRUD + module-specific logic.

| WBS | Module group | Modules (routes) | Key logic beyond CRUD |
| --- | --- | --- | --- |
| 4.1 | People & access | users, staff (+ shifts, attendance), training, profile | Role assignment, own-record scoping |
| 4.2 | Procurement | suppliers (+ deliveries), supplier-evaluations | Delivery quality/qty capture, evaluation scores |
| 4.3 | Inventory | materials/raw, materials/packaging | Min-stock thresholds, stock update service methods |
| 4.4 | Production | production, machines, fat (factory acceptance tests) | Transactional material deduction/restoration on create/edit/cancel/delete, batch numbering BN-YYYYMMDD-nnn, machine status coupling |
| 4.5 | Quality chain | quality (inspections), finished-goods, improvement (CAPA) | Approve/reject flow, FG creation by flavour/batch/expiry |
| 4.6 | Sales & finance | customers, sales, invoicing | Stock deduction on Completed orders with consistent restore/re-deduct on edit/delete; invoice totals/unpaid tracking |
| 4.7 | Utilities & compliance | waste, water (usage+tests), power (usage+generator log), certifications, permits, documents (upload/download), sops (templates + checklists + supervisor approval) | Expiry alerts, file-path containment, JSON checklist normalisation |
| 4.8 | Safety | safety, safety/hazards, safety/accidents, safety/drills, ppe | Open-incident KPIs, PPE expiry/replacement |
| 4.9 | Engineering | maintenance (+ reminders), efficiency (OEE) | Service-date reminder query, OEE averages/daily/monthly |

Effort: ≈ 200 h total (≈ 22 h per module group average).

## 5. Phase 5 — Cross-Cutting Features (May – Jun 2026)

| WBS | Work package | Deliverable |
| --- | --- | --- |
| 5.1 | Dashboard KPIs & charts (production by flavour, monthly sales/production, OEE, waste mix, open incidents) | Dashboard model + view |
| 5.2 | Notifications centre (low raw/packaging stock, expiring certificates/permits) | notifications module |
| 5.3 | Audit trail viewer with filters | audit module |
| 5.4 | Reports coverage per SRS Section 8 via module indexes + dashboard charts | report mapping table in project chapter |

## 6. Phase 6 — Integration, Testing & Repair (Jun – Jul 2026)

| WBS | Work package | Tasks | Deliverable |
| --- | --- | --- | --- |
| 6.1 | Static validation suite | lint all files, verify every view exists for every route/method, every model method called exists, every form field consumed | Validator (153 files scanned) |
| 6.2 | Integration test suite | schema ↔ query cross-check (38 tables, all columns referenced), RBAC matrix completeness, CSRF wiring | 101 automated checks |
| 6.3 | Live HTTP smoke testing | Scripted sessions per role: login, CRUD cycles, stock-consistency lifecycles, logout/reset round-trips | T1–T10 test log (all PASS) |
| 6.4 | Defect repair | Fix findings: SOP JSON fatal, document path traversal, sales/production stock consistency, dashboard incident stat, profile email persistence, maintenance reminder filter, packaging reorder alerts, batch-number suggestion | Repaired build |
| 6.5 | Regression | Re-run validator + 101 checks after every fix | Green suites |

## 7. Phase 7 — Deployment, Documentation & Handover (Jul – Aug 2026)

| WBS | Work package | Deliverable |
| --- | --- | --- |
| 7.1 | Production deployment guide | XAMPP install, DB import, environment config, URL & rewrite notes (user manual) |
| 7.2 | User manual | Role-based walkthroughs for all 8 roles |
| 7.3 | Academic documentation | Project chapter, SRS, WBS, Gantt chart (docs 01–05) |
| 7.4 | Operational hardening checklist | Change default passwords, configure SMTP, enable Apache/mod_rewrite, mysqld auto-start service |

Total estimated effort: ≈ 480 person-hours over 11 months.

Milestones: M1 SRS approved (Nov 2025) · M2 Design freeze + DB ready (Jan 2026) · M3 Login + first modules live (Feb 2026) · M4 All modules feature-complete (Jun 2026) · M5 Test-green repaired build (Jul 2026) · M6 Documentation pack delivered (Aug 2026).

# Work Package 12 - Hardening, Access Partitioning and Documentation (August 2026)

• Reports module rebuilt: role gate (Administrator + Factory Manager only) and department partitioning of the report catalogue.

• Dedicated print subsystem: clean printable documents for every report and for sales receipts (company letterhead + title + results only).

• Receipt flow: completing a sale now lands directly on a printable receipt; receipts printable per order.

• Input validation sweep: shared server-side numeric range guard wired into ten modules plus a global client-side validation net.

• Backup/restore corrected for MySQL implicit-commit-on-DDL behaviour; asset library self-hosted so the system runs fully offline.

• Deliverables: updated SRS (v2.1), prototype screen inventory, Gantt actuals, and this WBS revision.