# Project Gantt Chart

## Factory Management System for Fresh Fruit Juice Production — Actual Build Timeline

Derived from the real repository history at github.com/Apau247/freshjuice (branch main, 22 commits, 10 July – 6 August 2026, ≈ 20,969 insertions / 5,700 deletions).

## 1. Mermaid Gantt (renders on GitHub / VS Code / mermaid.live)

gantt

title Factory Management System — Actual Build History (Jul – Aug 2026)

dateFormat  YYYY-MM-DD

axisFormat  %d %b

section Foundation

Initial import - 146 files          :milestone, m1, 2026-07-10, 0d

Correction sweep (auth, RBAC, views):done, p1, 2026-07-10, 1d

section Expansion

Bulk feature development            :active, p2, 2026-07-11, 9d

Expansion checkpoint (93 files)     :milestone, m2, 2026-07-19, 0d

section Restructure and Theme

Folder restructure - 142 files      :p3, 2026-07-20, 2d

Glass theme, app.js, dashboard      :p3b, 2026-07-21, 1d

section Quality and Safety

Safety and quality workflow modules :p4, 2026-07-21, 4d

Pruning and consolidation           :p5, 2026-07-24, 5d

section Hardening

Enhancement pass                    :p6, 2026-07-29, 5d

Stabilisation reset - 52 files      :p7, 2026-08-02, 2d

Sidebar navigation UX               :p8, 2026-08-04, 1d

Cross-system integration            :crit, p9, 2026-08-04, 3d

Integrated release candidate        :milestone, m5, 2026-08-06, 0d

## 2. Weekly Tabular Gantt (weeks Mon 6 Jul → Sun 9 Aug 2026)

| Phase | Jul 6–12 | Jul 13–19 | Jul 20–26 | Jul 27–Aug 2 | Aug 3–9 |
| --- | --- | --- | --- | --- | --- |
| Foundation import + correction sweep | ██ |  |  |  |  |
| Bulk feature expansion | ▌ | ██ |  |  |  |
| Folder restructure + glass theming |  |  | ██ |  |  |
| Safety & quality workflow modules |  |  | ██ | ▌ |  |
| Pruning & consolidation |  |  | █▌ | ██ |  |
| Enhancement pass |  |  |  | ██ | ▌ |
| Stabilisation reset |  |  |  | █▌ |  |
| Sidebar navigation UX |  |  |  |  | ██ |
| Cross-system integration |  |  |  |  | ██ |

## 3. Phases Mapped to Commits

| Phase | Dates | Commits | Scale |
| --- | --- | --- | --- |
| P1 Foundation & correction sweep | 10 Jul 2026 | 359cdc2 initial import; b2df0b9 password hashes; 8b7de25 PpeModel ORDER BY; 609da92 staff view + New-button links; a46bf9d controller-view/form-field mismatches across 25 controllers + RBAC guards | 146-file import (10,434 LOC) then 78 files corrected |
| P2 Bulk feature expansion | 11–19 Jul 2026 | c7ec1d5 expansion checkpoint | 93 files, +4,388 / −1,687 |
| P3 Restructure & theming | 20–21 Jul 2026 | 0c4ef64 new structure (142 files); bd5ff48; 45004e0 new module; d1bdf0c glass.css/style.css/app.js/dashboard/layout | ~160 file touches |
| P4 Safety & quality workflows | 21–24 Jul 2026 | 9008b32 safety & quality features; 6d9ea8c; 1713546 | 73 files, +2,273 |
| P5 Pruning & consolidation | 24–29 Jul 2026 | c60a23e cleanup (−2,148); 1b5d142; 62203a5; 42d5b51; 64742c6; a915ba8 | ~105 files, net slimming |
| P6 Stabilisation | 2 Aug 2026 | 0779809 reset | 52 files, +641 / −116 |
| P7 Navigation UX | 4 Aug 2026 | 2334d80 sidebar update | +49 / −18 |
| P8 Cross-system integration | 4–6 Aug 2026 | f94da59 backend/frontend/controllers/models/config touchpoints | 41 files, +489 / −148 |

## 4. Milestones (actual dates)

| ID | Milestone | Date | Evidence |
| --- | --- | --- | --- |
| M1 | System baseline under version control | 10 Jul 2026 | Initial commit: 146 files, 10,434 lines |
| M2 | Interface contracts corrected (controllers ↔ views ↔ RBAC) | 10 Jul 2026 | Fix sweep across 25 controllers / 57 files |
| M3 | New structure + safety & quality workflows live | 21 Jul 2026 | Structure rename + 67-file feature commit |
| M4 | Stabilised codebase after consolidation | 2 Aug 2026 | Reset commit after pruning passes |
| M5 | Integrated release candidate | 6 Aug 2026 | Final cross-system integration commit |

## 5. Commit Log (complete, oldest first)

| # | Date | Hash | Message | Files | +/− |
| --- | --- | --- | --- | --- | --- |
| 1 | 2026-07-10 | 359cdc2 | Initial commit: Factory Management System | 146 | +10,434 |
| 2 | 2026-07-10 | b2df0b9 | Fix: correct password hashes to match password123 | 1 | +8/−8 |
| 3 | 2026-07-10 | 8b7de25 | Fix: PpeModel ORDER BY IssueDate → DateIssued | 1 | +1/−1 |
| 4 | 2026-07-10 | 609da92 | Fix: staff view variable + all New button links /form → /create | 19 | +28/−28 |
| 5 | 2026-07-10 | a46bf9d | Fix: controller-view variable & form-field mismatches (25 controllers) + RBAC button guards | 57 | +370/−303 |
| 6 | 2026-07-19 | c7ec1d5 | Expansion checkpoint | 93 | +4,388/−1,687 |
| 7 | 2026-07-21 | 0c4ef64 | New structure (folder reorganisation) | 142 | renamed |
| 8 | 2026-07-21 | bd5ff48 | New module additions | 15 | +812/−248 |
| 9 | 2026-07-21 | 45004e0 | New module | 2 | +395/−287 |
| 10 | 2026-07-21 | 6d9ea8c | Fixes | 5 | +906/−337 |
| 11 | 2026-07-21 | 1713546 | Save changes | 1 | +57/−31 |
| 12 | 2026-07-21 | d1bdf0c | Glass.css/style.css fixes, app.js performance, dashboard & layout improvements | 1 | +14/−21 |
| 13 | 2026-07-21 | 9008b32 | New workflow: safety and quality management features | 67 | +1,310/−167 |
| 14 | 2026-07-24 | c60a23e | Cleanup / pruning | 68 | +321/−2,148 |
| 15 | 2026-07-24 | 1b5d142 | Tweak | 1 | +1/−1 |
| 16 | 2026-07-24 | 62203a5 | Addition | 1 | +32 |
| 17 | 2026-07-24 | 42d5b51 | PHP tweak | 1 | +1/−1 |
| 18 | 2026-07-29 | 64742c6 | Enhancement pass | 25 | +452/−146 |
| 19 | 2026-07-29 | a915ba8 | Updates | 9 | +260/−4 |
| 20 | 2026-08-02 | 0779809 | Stabilisation reset | 52 | +641/−116 |
| 21 | 2026-08-04 | 2334d80 | Sidebar update | 1 | +49/−18 |
| 22 | 2026-08-06 | f94da59 | Cross-system integration: backend, frontend, controllers, models, configuration | 41 | +489/−148 |

## 6. Observations

• Development was checkpoint-driven: intense bursts followed by consolidation commits (19 Jul, 21 Jul, 24 Jul), typical of iterative solo work alongside factory duties.

• The largest single-day delivery was the initial import (10,434 lines), immediately hardened by an interface-contract correction sweep — validating the codebase before further growth.

• Net code volume grew from 10.4k to ≈ 21k inserted lines in four weeks, with deliberate pruning (−2,148 lines on 24 Jul) keeping the tree lean.

# Actual timeline - hardening increment (August 2026)

• Reports access control and department partitioning implemented and integration-tested (ReportModel::DEPARTMENT_OF, ReportController guard).

• Print subsystem delivered: layouts/print.php shell + reports/print and sales/receipt documents; legacy page-print CSS removed.

• Validation sweep: Controller::checkNumber wired into ten controllers; 32 form inputs given min/max/step constraints; global JS submit validator shipped.

• Backup/restore corrected for implicit-DDL commits; verified with a live backup-download then restore round-trip.

• Front-end assets vendored locally (frontend/assets/vendor) and .gitignore scoped so offline installs clone correctly.

• Documentation set revised to match the running product (WBS, SRS v2.1, chapter, prototype appendix, this chart, user manual).